## Sheet1
Iteration | Task | Priority | Role | Name | Status | Notes
Iteration02 | Activate Surprise cell in easy game mode | P1 | Developer | Jihad | Completed |  | instructions
| Activate Surprise cell in medium game mode | P1 | Developer | Jihad | Completed |  | - download this scrum report template
| Activate Surprise cell in hard game mode | P1 | Developer | Jihad | Completed |  | - at the start of each iteration fill in the tasks
| Validate a correct surrprise cell activation sequences - Score, hearts and mark as used(blocked) | P2 | Developer | Jihad | Completed |  | - during iteration update the status
| Activate question cell in easy game mode | P1 | Developer | Jihad | Completed
| Activate question cell in medium game mode | P1 | Developer | Jihad | Completed
| Activate question cell in hard game mode | P1 | Developer | Jihad | Completed
| Validate a correct question cell activation sequences - Score, hearts and mark as used(blocked) | P2 | Developer | Jihad | Completed
| Create a pop up for a question once activating a surprise cell. | P2 | Developer | Jihad | Completed
| Provide a feedback on system behaviour according to question answer(right or wrong answer) | P2 | Developer | Jihad | Completed
| Create end game screen - lose game case | P2 | Developer | Jihad | Completed
| Block mine cell after reveal | P1 | Developer | Jihad | Completed
| Added back-navigation buttons to the Boards and History screens. | P2 | Developer | Adan | Completed
| Improved UI styling for the History screen (ComboBoxes + DatePicker) | P3 | Developer | Adan | Completed
| Updated flagging logic to correctly add or deduct score based on flagging a mine or a non-mine cell. | P1 | Developer | Adan | Completed
| Extended cascade reveal logic to include Question and Surprise cells. | P1 | Developer | Adan | Completed
| Enhanced Board UI: added player avatars and unique colors for each board. | P2 | Developer | Adan | Completed
| Implemented flag count limit per difficulty to prevent cheating by flagging all cells. | P1 | Developer | Adan | Completed
| Added avatars to the History screen and saved avatar paths in the CSV as part of the Game record. | P2 | Developer | Adan | Completed
| Added a new game result type: GIVE_UP, displayed and saved in History | P1 | Developer | Adan | Completed
| Implemented exception handling (alerts) for invalid filters in the History screen. | P2 | Developer | Adan | Completed
| Design Filters screen layout (FXML UI) | P3 | Developer | Aya | Completed | Designed Filters screen using FXML (GridPane, VBox, HBox), including title, icons, back button, and toggle switches with consistent styling
| Implement global Music & Sound control | P3 | Developer | Aya | Completed | Connected Music and Sound toggles to SysData and SoundManager, so changes affect the entire application globally
| Synchronize UI state across all screens | P3 | Developer | Aya | Completed | When Music/Sound is turned OFF in Filters, all screens reflect the muted state visually (music/sound icons) and functionally (no sound playback)
| Implement Timer filter logic | P3 | Developer | Aya | Completed | Implemented onTimerToggled() to update global timer configuration in SysData, affecting gameplay behavior
| Sync Filters UI with saved settings | P3 | Developer | Aya | Completed | Implemented initialize() to load saved configuration from SysData and display correct toggle states when entering the Filters screen
| Implement navigation back to Settings screen | P3 | Developer | Aya | Completed | Implemented back navigation using FXMLLoader and scene switching, including click sound feedback
| Add UI placeholders for future filters | P3 | Developer | Aya | Completed | Smart Hints and Auto Remove Flag toggles exist in UI and update SysData, but are not yet connected to active game logic
| Separate music and sound effects control | P3 | Developer | Aya | Completed | Split audio control into two independent channels: background music has its own logo and toggle, while UI sound effects (clicks) use a separate logo and Sound filter